## Modules
Module | Stage | Confidence
Customer ETL | 3 | High
Billing ETL | 2 | Medium
Risk ETL | 4 | High
Finance ETL | 1 | Low

## Utilities
Utility Group | Examples | Progress | Status | Details
Validation Framework | Reconciliation, Golden Dataset Diff | 75 | In Progress | Row-level validation implemented
Runtime Framework | Retry, Restart, Logging | 60 | In Progress | Recovery semantics partially implemented
Optimization Framework | Join Tuning, Partition Helpers | 30 | Planned | Pending benchmark integration
Developer Tooling | DAG Visualization, Diagnostics | 50 | In Progress | Graph viewer operational
Metadata Framework | Schema Resolution, Param Binding | 80 | Complete | Fully integrated across modules